## Sprint Plan
Epic ID | Epic Description | Feature ID | Feature Description | User Story ID | User Story Description | Priority | Developer Assigned | Sprint | Timeline | Mockup URL
AUTH | Authentication & Host Onboarding | FEAT-AUTH-01 | Landing & entry points | US-AUTH-001 | As a first-time visitor, I want to land on a marketing page that explains SafalEvents and offers clear actions to explore events or become a host, so that I understand the product and know how to start. | Medium | Developer 1 | S1 | Sprint 1 · 22 Jun 2026 – 03 Jul 2026 | Web: https://safal-events.vercel.app/
AUTH | Authentication & Host Onboarding | FEAT-AUTH-02 | Host registration (individual & organization) | US-AUTH-002 | As a prospective host, I want to register with my first/last name, email, phone and password as an "individual" host, so that I can create and manage my own events. | High | Developer 2 | S1 | Sprint 1 · 22 Jun 2026 – 03 Jul 2026 | Web: https://safal-events.vercel.app/
AUTH | Authentication & Host Onboarding | FEAT-AUTH-02 | Host registration (individual & organization) | US-AUTH-003 | As a organization representative, I want to register my organization (name, type, website, country, city, state) and upload verification documents, so that my organization can host events under a verified profile. | High | Developer 2 | S1 | Sprint 1 · 22 Jun 2026 – 03 Jul 2026 | Web: https://safal-events.vercel.app/
AUTH | Authentication & Host Onboarding | FEAT-AUTH-03 | OTP verification (email + SMS) | US-AUTH-004 | As a registering user, I want to confirm my identity with a one-time code sent to my email and phone, so that only verified people can create accounts or RSVP. | High | Developer 3 | S1 | Sprint 1 · 22 Jun 2026 – 03 Jul 2026 | Web: https://safal-events.vercel.app/
AUTH | Authentication & Host Onboarding | FEAT-AUTH-04 | Sign-in, session & account states | US-AUTH-005 | As a registered user (guest/host/admin), I want to log in with my credentials and be routed to the correct dashboard for my role, so that I get a role-appropriate experience. | High | Developer 4 | S1 | Sprint 1 · 22 Jun 2026 – 03 Jul 2026 | Web: https://safal-events.vercel.app/
AUTH | Authentication & Host Onboarding | FEAT-AUTH-04 | Sign-in, session & account states | US-AUTH-006 | As a organization host awaiting approval / suspended host, I want to be informed why I cannot access the host dashboard, so that I understand my account state and next steps. | High | Developer 4 | S1 | Sprint 1 · 22 Jun 2026 – 03 Jul 2026 | Web: https://safal-events.vercel.app/
AUTH | Authentication & Host Onboarding | FEAT-AUTH-04 | Sign-in, session & account states | US-AUTH-007 | As a signed-in user, I want to end my session securely, so that my account is protected on shared devices. | Medium | Developer 4 | S1 | Sprint 1 · 22 Jun 2026 – 03 Jul 2026 | Web: https://safal-events.vercel.app/
EVENT | Event Creation & Management (Host) | FEAT-EVENT-01 | Event authoring (details & questions) | US-EVENT-001 | As a host, I want to enter title, date, time, venue/location, city, state, description, cover image, theme and event type, so that my event has a complete public listing. | High | Developer 5 | S2 | Sprint 2 · 06 Jul 2026 – 17 Jul 2026 | Web: https://safal-events.vercel.app/
EVENT | Event Creation & Management (Host) | FEAT-EVENT-01 | Event authoring (details & questions) | US-EVENT-003 | As a host, I want to add custom questions guests must answer when they RSVP, so that I collect information I need (allergies, song requests, startup details). | Medium | Developer 5 | S2 | Sprint 2 · 06 Jul 2026 – 17 Jul 2026 | Web: https://safal-events.vercel.app/
EVENT | Event Creation & Management (Host) | FEAT-EVENT-02 | Capacity, approval & RSVP rules | US-EVENT-002 | As a host, I want to define maximum capacity and whether RSVPs require my approval, so that I control attendance volume and who gets in. | High | Developer 1 | S2 | Sprint 2 · 06 Jul 2026 – 17 Jul 2026 | Web: https://safal-events.vercel.app/
EVENT | Event Creation & Management (Host) | FEAT-EVENT-02 | Capacity, approval & RSVP rules | US-EVENT-005 | As a host, I want to set an RSVP deadline, max guests per RSVP, self-edit, self-cancellation, cancellation cut-off and whether a cancellation reason is required, so that RSVP behaviour matches my event policy. | High | Developer 1 | S2 | Sprint 2 · 06 Jul 2026 – 17 Jul 2026 | Web: https://safal-events.vercel.app/
EVENT | Event Creation & Management (Host) | FEAT-EVENT-03 | Visibility, engagement & paid tickets | US-EVENT-004 | As a host, I want to set the event privacy (public/private/unlisted), whether the guest list is shown and how RSVP counts are displayed, so that I control how much is public. | Medium | Developer 2 | S2 | Sprint 2 · 06 Jul 2026 – 17 Jul 2026 | Web: https://safal-events.vercel.app/
EVENT | Event Creation & Management (Host) | FEAT-EVENT-03 | Visibility, engagement & paid tickets | US-EVENT-006 | As a host, I want to toggle comments, photo uploads and guest confirmation for the event, so that I enable the right interaction level. | Medium | Developer 2 | S2 | Sprint 2 · 06 Jul 2026 – 17 Jul 2026 | Web: https://safal-events.vercel.app/
EVENT | Event Creation & Management (Host) | FEAT-EVENT-03 | Visibility, engagement & paid tickets | US-EVENT-007 | As a host, I want to turn on payments and set a ticket price for the event, so that I can monetize attendance. | Medium | Developer 2 | S2 | Sprint 2 · 06 Jul 2026 – 17 Jul 2026 | Web: https://safal-events.vercel.app/
EVENT | Event Creation & Management (Host) | FEAT-EVENT-04 | Event lifecycle (publish/edit/clone/delete) | US-EVENT-008 | As a host, I want to publish an event live or keep it as a draft, so that I can prepare events before making them public. | High | Developer 3 | S2 | Sprint 2 · 06 Jul 2026 – 17 Jul 2026 | Web: https://safal-events.vercel.app/
EVENT | Event Creation & Management (Host) | FEAT-EVENT-04 | Event lifecycle (publish/edit/clone/delete) | US-EVENT-009 | As a host, I want to update event details after publishing and have guests informed of meaningful changes, so that attendees always have accurate information. | High | Developer 3 | S2 | Sprint 2 · 06 Jul 2026 – 17 Jul 2026 | Web: https://safal-events.vercel.app/
EVENT | Event Creation & Management (Host) | FEAT-EVENT-04 | Event lifecycle (publish/edit/clone/delete) | US-EVENT-010 | As a host, I want to clone an existing event as a starting point, so that I can launch recurring/similar events quickly. | Low | Developer 3 | S2 | Sprint 2 · 06 Jul 2026 – 17 Jul 2026 | Web: https://safal-events.vercel.app/
EVENT | Event Creation & Management (Host) | FEAT-EVENT-04 | Event lifecycle (publish/edit/clone/delete) | US-EVENT-011 | As a host, I want to remove an event and notify registered guests of cancellation, so that I can call off events cleanly. | Medium | Developer 3 | S2 | Sprint 2 · 06 Jul 2026 – 17 Jul 2026 | Web: https://safal-events.vercel.app/
EVENT | Event Creation & Management (Host) | FEAT-EVENT-05 | Public host profile | US-EVENT-012 | As a guest, I want to view a host's public profile and their events, so that I can judge credibility before RSVPing. | Low | Developer 4 | S2 | Sprint 2 · 06 Jul 2026 – 17 Jul 2026 | Web: https://safal-events.vercel.app/
DISC | Event Discovery (Guest) | FEAT-DISC-01 | Browse, search & filter events | US-DISC-001 | As a visitor or guest, I want to see a gallery of published events, so that I can find something to attend. | High | Developer 5 | S3 | Sprint 3 · 20 Jul 2026 – 31 Jul 2026 | Web: https://safal-events.vercel.app/
DISC | Event Discovery (Guest) | FEAT-DISC-01 | Browse, search & filter events | US-DISC-002 | As a guest, I want to search events by title or keyword, so that I quickly find a specific event. | Medium | Developer 5 | S3 | Sprint 3 · 20 Jul 2026 – 31 Jul 2026 | Web: https://safal-events.vercel.app/
DISC | Event Discovery (Guest) | FEAT-DISC-01 | Browse, search & filter events | US-DISC-003 | As a guest, I want to filter by city/state/type and sort by distance, date or rating, so that I see the most relevant events first. | Medium | Developer 5 | S3 | Sprint 3 · 20 Jul 2026 – 31 Jul 2026 | Web: https://safal-events.vercel.app/
DISC | Event Discovery (Guest) | FEAT-DISC-02 | Event detail page & view tracking | US-DISC-004 | As a guest, I want to open an event to see full details, host, ratings and (if allowed) the guest list, so that I have everything I need to decide. | High | Developer 1 | S3 | Sprint 3 · 20 Jul 2026 – 31 Jul 2026 | Web: https://safal-events.vercel.app/
DISC | Event Discovery (Guest) | FEAT-DISC-02 | Event detail page & view tracking | US-DISC-005 | As a host (beneficiary), I want to each event-page visit to be counted, so that I can measure interest via analytics. | Low | Developer 1 | S3 | Sprint 3 · 20 Jul 2026 – 31 Jul 2026 | Web: https://safal-events.vercel.app/
RSVP | RSVP & Ticketing (Guest) | FEAT-RSVP-01 | RSVP intake & OTP verification | US-RSVP-001 | As a guest, I want to begin an RSVP and select going, maybe or decline, so that I can register my intent to attend. | High | Developer 2 | S3 | Sprint 3 · 20 Jul 2026 – 31 Jul 2026 | Web: https://safal-events.vercel.app/
RSVP | RSVP & Ticketing (Guest) | FEAT-RSVP-01 | RSVP intake & OTP verification | US-RSVP-002 | As a guest, I want to confirm my email/phone with a one-time code before my RSVP is recorded, so that RSVPs are trustworthy and reduce spam. | High | Developer 2 | S3 | Sprint 3 · 20 Jul 2026 – 31 Jul 2026 | Web: https://safal-events.vercel.app/
RSVP | RSVP & Ticketing (Guest) | FEAT-RSVP-02 | Party size, questions & preferences | US-RSVP-003 | As a guest, I want to specify how many guests I am bringing up to the allowed maximum, so that my whole party is counted. | Medium | Developer 3 | S3 | Sprint 3 · 20 Jul 2026 – 31 Jul 2026 | Web: https://safal-events.vercel.app/
RSVP | RSVP & Ticketing (Guest) | FEAT-RSVP-02 | Party size, questions & preferences | US-RSVP-004 | As a guest, I want to answer the host's custom questions during RSVP, so that the host gets the details they requested. | Medium | Developer 3 | S3 | Sprint 3 · 20 Jul 2026 – 31 Jul 2026 | Web: https://safal-events.vercel.app/
RSVP | RSVP & Ticketing (Guest) | FEAT-RSVP-02 | Party size, questions & preferences | US-RSVP-005 | As a guest, I want to select my preferred channel (email/SMS), reminder schedule and opt out of SMS, so that I receive notifications the way I prefer. | Low | Developer 3 | S3 | Sprint 3 · 20 Jul 2026 – 31 Jul 2026 | Web: https://safal-events.vercel.app/
RSVP | RSVP & Ticketing (Guest) | FEAT-RSVP-03 | Capacity, waitlist & approval intake | US-RSVP-006 | As a guest, I want to be placed on a waitlist when the event is at capacity, so that I still have a chance if a spot frees up. | High | Developer 4 | S3 | Sprint 3 · 20 Jul 2026 – 31 Jul 2026 | Web: https://safal-events.vercel.app/
RSVP | RSVP & Ticketing (Guest) | FEAT-RSVP-03 | Capacity, waitlist & approval intake | US-RSVP-007 | As a guest, I want to submit my RSVP for host approval when the event requires it, so that I understand my attendance is pending. | Medium | Developer 4 | S3 | Sprint 3 · 20 Jul 2026 – 31 Jul 2026 | Web: https://safal-events.vercel.app/
RSVP | RSVP & Ticketing (Guest) | FEAT-RSVP-04 | Payment & confirmation | US-RSVP-008 | As a guest, I want to pay the ticket price (per guest) when RSVPing to a paid event, so that I secure my paid spot. | Medium | Developer 5 | S3 | Sprint 3 · 20 Jul 2026 – 31 Jul 2026 | Web: https://safal-events.vercel.app/
RSVP | RSVP & Ticketing (Guest) | FEAT-RSVP-04 | Payment & confirmation | US-RSVP-009 | As a guest, I want to get a confirmation with my booking ID and a manage-RSVP link, so that I have proof and can manage my RSVP. | High | Developer 5 | S3 | Sprint 3 · 20 Jul 2026 – 31 Jul 2026 | Web: https://safal-events.vercel.app/
RSVP | RSVP & Ticketing (Guest) | FEAT-RSVP-05 | RSVP deadline enforcement | US-RSVP-010 | As a guest, I want to be prevented from RSVPing after the deadline, so that expectations about closing are clear. | Medium | Developer 1 | S3 | Sprint 3 · 20 Jul 2026 – 31 Jul 2026 | Web: https://safal-events.vercel.app/
GUEST | Guest Dashboard & Self-Service | FEAT-GUEST-01 | My RSVPs & digital pass | US-GUEST-001 | As a guest, I want to see my upcoming and past events in one place, so that I can keep track of what I'm attending. | High | Developer 2 | S4 | Sprint 4 · 03 Aug 2026 – 14 Aug 2026 | Web: https://safal-events.vercel.app/
GUEST | Guest Dashboard & Self-Service | FEAT-GUEST-01 | My RSVPs & digital pass | US-GUEST-002 | As a guest, I want to view my booking ID and QR pass for an event, so that I can be checked in quickly on arrival. | High | Developer 2 | S4 | Sprint 4 · 03 Aug 2026 – 14 Aug 2026 | Web: https://safal-events.vercel.app/
GUEST | Guest Dashboard & Self-Service | FEAT-GUEST-02 | Self-service edit & cancel | US-GUEST-003 | As a guest, I want to change my guest count or status when self-edit is allowed, so that I can keep my RSVP accurate. | Medium | Developer 3 | S4 | Sprint 4 · 03 Aug 2026 – 14 Aug 2026 | Web: https://safal-events.vercel.app/
GUEST | Guest Dashboard & Self-Service | FEAT-GUEST-02 | Self-service edit & cancel | US-GUEST-004 | As a guest, I want to cancel my attendance subject to the host's rules, so that I free my spot when I can't attend. | Medium | Developer 3 | S4 | Sprint 4 · 03 Aug 2026 – 14 Aug 2026 | Web: https://safal-events.vercel.app/
GUEST | Guest Dashboard & Self-Service | FEAT-GUEST-03 | Guest messaging & broadcasts | US-GUEST-005 | As a guest, I want to send messages to the host of an event I'm attending and see replies, so that I can ask questions and get answers. | Medium | Developer 4 | S4 | Sprint 4 · 03 Aug 2026 – 14 Aug 2026 | Web: https://safal-events.vercel.app/
GUEST | Guest Dashboard & Self-Service | FEAT-GUEST-03 | Guest messaging & broadcasts | US-GUEST-006 | As a guest, I want to receive announcements, reminders and update notices from the host, so that I stay informed about the event. | Medium | Developer 4 | S4 | Sprint 4 · 03 Aug 2026 – 14 Aug 2026 | Web: https://safal-events.vercel.app/
GUEST | Guest Dashboard & Self-Service | FEAT-GUEST-04 | Post-event feedback | US-GUEST-007 | As a guest, I want to rate the event and leave comments after it ends, so that I help the host improve and inform other guests. | Medium | Developer 5 | S4 | Sprint 4 · 03 Aug 2026 – 14 Aug 2026 | Web: https://safal-events.vercel.app/
GM | Guest Management & Check-in (Host) | FEAT-GM-01 | Attendee list & filtering | US-GM-001 | As a host, I want to see all RSVPs with status, guest counts and answers, with search/filter, so that I understand and manage my attendees. | High | Developer 1 | S5 | Sprint 5 · 17 Aug 2026 – 28 Aug 2026 | Web: https://safal-events.vercel.app/
GM | Guest Management & Check-in (Host) | FEAT-GM-02 | Approvals & status management | US-GM-002 | As a host, I want to approve or decline pending RSVPs for approval-required events, so that I curate my attendee list. | High | Developer 2 | S5 | Sprint 5 · 17 Aug 2026 – 28 Aug 2026 | Web: https://safal-events.vercel.app/
GM | Guest Management & Check-in (Host) | FEAT-GM-02 | Approvals & status management | US-GM-003 | As a host, I want to manually change a guest's status and have the waitlist promote automatically when spots free up, so that my attendee list stays correct and full. | High | Developer 2 | S5 | Sprint 5 · 17 Aug 2026 – 28 Aug 2026 | Web: https://safal-events.vercel.app/
GM | Guest Management & Check-in (Host) | FEAT-GM-03 | Check-in | US-GM-004 | As a host, I want to check guests in via QR scan or manual toggle at the event, so that I track real attendance. | High | Developer 3 | S5 | Sprint 5 · 17 Aug 2026 – 28 Aug 2026 | Web: https://safal-events.vercel.app/
GM | Guest Management & Check-in (Host) | FEAT-GM-04 | Manual invites & broadcasts | US-GM-005 | As a host, I want to add a guest directly to the going list without them self-registering, so that I can include VIPs and offline invitees. | Medium | Developer 4 | S5 | Sprint 5 · 17 Aug 2026 – 28 Aug 2026 | Web: https://safal-events.vercel.app/
GM | Guest Management & Check-in (Host) | FEAT-GM-04 | Manual invites & broadcasts | US-GM-006 | As a host, I want to send an announcement to all guests of an event, so that I can share urgent or important updates at once. | Medium | Developer 4 | S5 | Sprint 5 · 17 Aug 2026 – 28 Aug 2026 | Web: https://safal-events.vercel.app/
ENG | Engagement (Comments, Polls, Photos) | FEAT-ENG-01 | Comments & moderation | US-ENG-001 | As a guest, I want to post comments on an event and read others' comments, so that I can engage with the community around the event. | Medium | Developer 5 | S8 | Sprint 8 · 28 Sep 2026 – 09 Oct 2026 | Web: https://safal-events.vercel.app/
ENG | Engagement (Comments, Polls, Photos) | FEAT-ENG-01 | Comments & moderation | US-ENG-002 | As a guest, I want to add emoji reactions to comments, so that I can respond lightweight without posting. | Low | Developer 5 | S8 | Sprint 8 · 28 Sep 2026 – 09 Oct 2026 | Web: https://safal-events.vercel.app/
ENG | Engagement (Comments, Polls, Photos) | FEAT-ENG-01 | Comments & moderation | US-ENG-003 | As a host, I want to pin important comments and delete inappropriate ones, so that I keep the board useful and clean. | Medium | Developer 5 | S8 | Sprint 8 · 28 Sep 2026 – 09 Oct 2026 | Web: https://safal-events.vercel.app/
ENG | Engagement (Comments, Polls, Photos) | FEAT-ENG-02 | Polls & voting | US-ENG-004 | As a host and guest, I want to the host to create polls and guests to vote on options, so that the host gathers preferences and guests feel involved. | Medium | Developer 1 | S8 | Sprint 8 · 28 Sep 2026 – 09 Oct 2026 | Web: https://safal-events.vercel.app/
ENG | Engagement (Comments, Polls, Photos) | FEAT-ENG-03 | Guest photo uploads | US-ENG-005 | As a guest, I want to upload photos to an event when the host allows it, so that attendees can share memories. | Low | Developer 2 | S8 | Sprint 8 · 28 Sep 2026 – 09 Oct 2026 | Web: https://safal-events.vercel.app/
NOTIF | Notifications & Templates Engine | FEAT-NOTIF-01 | Automated lifecycle messaging | US-NOTIF-001 | As a guest, I want to receive an automatic confirmation when I RSVP, so that I immediately know my registration succeeded. | High | Developer 3 | S6 | Sprint 6 · 31 Aug 2026 – 11 Sep 2026 | Web: https://safal-events.vercel.app/
NOTIF | Notifications & Templates Engine | FEAT-NOTIF-01 | Automated lifecycle messaging | US-NOTIF-002 | As a guest, I want to receive reminders before the event, so that I don't forget to attend. | High | Developer 3 | S6 | Sprint 6 · 31 Aug 2026 – 11 Sep 2026 | Web: https://safal-events.vercel.app/
NOTIF | Notifications & Templates Engine | FEAT-NOTIF-01 | Automated lifecycle messaging | US-NOTIF-003 | As a guest, I want to be invited to give feedback after the event, so that I can share my experience. | Medium | Developer 3 | S6 | Sprint 6 · 31 Aug 2026 – 11 Sep 2026 | Web: https://safal-events.vercel.app/
NOTIF | Notifications & Templates Engine | FEAT-NOTIF-01 | Automated lifecycle messaging | US-NOTIF-005 | As a guest, I want to be notified the moment I'm promoted from the waitlist, so that I can claim my newly available spot. | Medium | Developer 3 | S6 | Sprint 6 · 31 Aug 2026 – 11 Sep 2026 | Web: https://safal-events.vercel.app/
NOTIF | Notifications & Templates Engine | FEAT-NOTIF-02 | Update & cancellation notices | US-NOTIF-004 | As a guest, I want to be told when event details change or the event is cancelled, so that I always have correct information. | High | Developer 4 | S6 | Sprint 6 · 31 Aug 2026 – 11 Sep 2026 | Web: https://safal-events.vercel.app/
NOTIF | Notifications & Templates Engine | FEAT-NOTIF-03 | Host activity inbox | US-NOTIF-006 | As a host, I want to see a feed of new RSVPs, payments, check-ins, messages and capacity alerts, so that I stay on top of event activity. | High | Developer 5 | S6 | Sprint 6 · 31 Aug 2026 – 11 Sep 2026 | Web: https://safal-events.vercel.app/
NOTIF | Notifications & Templates Engine | FEAT-NOTIF-04 | Templates & delivery outbox | US-NOTIF-007 | As a host, I want to edit the subject and body of my event's notification templates using variables, so that messaging matches my voice and event. | Medium | Developer 1 | S6 | Sprint 6 · 31 Aug 2026 – 11 Sep 2026 | Web: https://safal-events.vercel.app/
NOTIF | Notifications & Templates Engine | FEAT-NOTIF-04 | Templates & delivery outbox | US-NOTIF-008 | As a host, I want to review a log of all messages sent for my event, so that I can audit and troubleshoot communications. | Medium | Developer 1 | S6 | Sprint 6 · 31 Aug 2026 – 11 Sep 2026 | Web: https://safal-events.vercel.app/
PAY | Payments & Payouts (Host) | FEAT-PAY-01 | Paid ticketing, transactions & revenue | US-PAY-001 | As a host, I want to enable payments and set a ticket price, so that I can sell tickets to my event. | Medium | Developer 2 | S7 | Sprint 7 · 14 Sep 2026 – 25 Sep 2026 | Web: https://safal-events.vercel.app/
PAY | Payments & Payouts (Host) | FEAT-PAY-01 | Paid ticketing, transactions & revenue | US-PAY-002 | As a host, I want to have each paid RSVP recorded as a transaction, so that I have an accurate sales record. | Medium | Developer 2 | S7 | Sprint 7 · 14 Sep 2026 – 25 Sep 2026 | Web: https://safal-events.vercel.app/
PAY | Payments & Payouts (Host) | FEAT-PAY-01 | Paid ticketing, transactions & revenue | US-PAY-003 | As a host, I want to see total revenue and a transaction breakdown for an event, so that I understand financial performance. | Low | Developer 2 | S7 | Sprint 7 · 14 Sep 2026 – 25 Sep 2026 | Web: https://safal-events.vercel.app/
PAY | Payments & Payouts (Host) | FEAT-PAY-02 | Payouts & receipts | US-PAY-004 | As a host, I want to save my bank account details to receive payouts, so that I can be paid for ticket sales. | Low | Developer 3 | S7 | Sprint 7 · 14 Sep 2026 – 25 Sep 2026 | Web: https://safal-events.vercel.app/
PAY | Payments & Payouts (Host) | FEAT-PAY-02 | Payouts & receipts | US-PAY-005 | As a guest, I want to receive a receipt for my ticket purchase, so that I have proof of payment. | Medium | Developer 3 | S7 | Sprint 7 · 14 Sep 2026 – 25 Sep 2026 | Web: https://safal-events.vercel.app/
ANALYTICS | Analytics & Reporting (Host) | FEAT-ANALYTICS-01 | Engagement & attendance analytics | US-ANALYTICS-001 | As a host, I want to see how many people viewed my event versus how many RSVP'd, so that I can gauge conversion and reach. | Medium | Developer 4 | S8 | Sprint 8 · 28 Sep 2026 – 09 Oct 2026 | Web: https://safal-events.vercel.app/
ANALYTICS | Analytics & Reporting (Host) | FEAT-ANALYTICS-01 | Engagement & attendance analytics | US-ANALYTICS-002 | As a host, I want to see counts by status and the check-in rate, so that I can plan logistics and measure turnout. | Medium | Developer 4 | S8 | Sprint 8 · 28 Sep 2026 – 09 Oct 2026 | Web: https://safal-events.vercel.app/
ANALYTICS | Analytics & Reporting (Host) | FEAT-ANALYTICS-02 | Feedback & revenue analytics | US-ANALYTICS-003 | As a host, I want to see aggregated ratings and feedback comments, so that I can evaluate guest satisfaction. | Low | Developer 5 | S8 | Sprint 8 · 28 Sep 2026 – 09 Oct 2026 | Web: https://safal-events.vercel.app/
ANALYTICS | Analytics & Reporting (Host) | FEAT-ANALYTICS-02 | Feedback & revenue analytics | US-ANALYTICS-004 | As a host, I want to see total revenue for paid events, so that I can measure commercial success. | Low | Developer 5 | S8 | Sprint 8 · 28 Sep 2026 – 09 Oct 2026 | Web: https://safal-events.vercel.app/
ADMIN | Admin Console | FEAT-ADMIN-01 | User & host oversight | US-ADMIN-001 | As a admin, I want to see all registered users/hosts with their type and status, so that I have oversight of the platform's accounts. | High | Developer 1 | S8 | Sprint 8 · 28 Sep 2026 – 09 Oct 2026 | Web: https://safal-events.vercel.app/
ADMIN | Admin Console | FEAT-ADMIN-02 | Host approvals & suspensions | US-ADMIN-002 | As a admin, I want to review pending organization hosts and approve or reject with a reason, so that only legitimate organizations can host. | High | Developer 2 | S8 | Sprint 8 · 28 Sep 2026 – 09 Oct 2026 | Web: https://safal-events.vercel.app/
ADMIN | Admin Console | FEAT-ADMIN-02 | Host approvals & suspensions | US-ADMIN-003 | As a admin, I want to suspend a host (with reason) and later reinstate them, so that I can enforce policy and protect guests. | High | Developer 2 | S8 | Sprint 8 · 28 Sep 2026 – 09 Oct 2026 | Web: https://safal-events.vercel.app/
ADMIN | Admin Console | FEAT-ADMIN-03 | System templates & platform settings | US-ADMIN-004 | As a admin, I want to edit platform default notification templates with versioning, so that consistent baseline messaging across all events. | Medium | Developer 3 | S8 | Sprint 8 · 28 Sep 2026 – 09 Oct 2026 | Web: https://safal-events.vercel.app/
ADMIN | Admin Console | FEAT-ADMIN-03 | System templates & platform settings | US-ADMIN-005 | As a admin, I want to set platform name, primary color, from-name, support email, SMS sender ID and RSVP defaults, so that I control global branding and defaults. | Medium | Developer 3 | S8 | Sprint 8 · 28 Sep 2026 – 09 Oct 2026 | Web: https://safal-events.vercel.app/
ADMIN | Admin Console | FEAT-ADMIN-04 | Logs, audit & event oversight | US-ADMIN-006 | As a admin, I want to audit OTP verification attempts with outcome, IP and device, so that I can detect abuse and support users. | Medium | Developer 4 | S8 | Sprint 8 · 28 Sep 2026 – 09 Oct 2026 | Web: https://safal-events.vercel.app/
ADMIN | Admin Console | FEAT-ADMIN-04 | Logs, audit & event oversight | US-ADMIN-007 | As a admin, I want to see a chronological, tamper-evident record of key actions, so that I have accountability and traceability. | Medium | Developer 4 | S8 | Sprint 8 · 28 Sep 2026 – 09 Oct 2026 | Web: https://safal-events.vercel.app/
ADMIN | Admin Console | FEAT-ADMIN-04 | Logs, audit & event oversight | US-ADMIN-008 | As a admin, I want to view all events and platform-level analytics, so that I can monitor and moderate activity. | Low | Developer 4 | S8 | Sprint 8 · 28 Sep 2026 – 09 Oct 2026 | Web: https://safal-events.vercel.app/
APPROVAL | RSVP Approval Workflow | FEAT-APPROVAL-01 | Under-Approval lifecycle (approve/reject/reopen) | US-APPROVAL-001 | As a guest, I want to have my RSVP held as 'Under Approval' when the event requires organizer approval, so that I know my spot is pending the host's decision. | High | Developer 5 | S4 | Sprint 4 · 03 Aug 2026 – 14 Aug 2026 | Web: https://safal-events.vercel.app/
APPROVAL | RSVP Approval Workflow | FEAT-APPROVAL-01 | Under-Approval lifecycle (approve/reject/reopen) | US-APPROVAL-002 | As a host or permitted staff, I want to review pending RSVPs and approve or reject each (optionally with a reason), so that I curate exactly who is admitted. | High | Developer 5 | S4 | Sprint 4 · 03 Aug 2026 – 14 Aug 2026 | Web: https://safal-events.vercel.app/
APPROVAL | RSVP Approval Workflow | FEAT-APPROVAL-01 | Under-Approval lifecycle (approve/reject/reopen) | US-APPROVAL-003 | As a host, I want to move a rejected RSVP back into the pending queue, so that I can reverse a decision if circumstances change. | Low | Developer 5 | S4 | Sprint 4 · 03 Aug 2026 – 14 Aug 2026 | Web: https://safal-events.vercel.app/
APPROVAL | RSVP Approval Workflow | FEAT-APPROVAL-02 | Capacity-driven waitlist approval | US-APPROVAL-004 | As a guest, I want to be waitlisted and held for approval when the event is full, so that I still have a chance if a seat frees up. | High | Developer 1 | S4 | Sprint 4 · 03 Aug 2026 – 14 Aug 2026 | Web: https://safal-events.vercel.app/
APPROVAL | RSVP Approval Workflow | FEAT-APPROVAL-03 | Approval emails, status & history | US-APPROVAL-005 | As a guest and host, I want to the right email at each step of the approval lifecycle, so that both sides always know the current state. | High | Developer 2 | S4 | Sprint 4 · 03 Aug 2026 – 14 Aug 2026 | Web: https://safal-events.vercel.app/
APPROVAL | RSVP Approval Workflow | FEAT-APPROVAL-03 | Approval emails, status & history | US-APPROVAL-006 | As a guest, I want to see my approval state consistently wherever my RSVP appears, so that there is no ambiguity about whether I'm in. | Medium | Developer 2 | S4 | Sprint 4 · 03 Aug 2026 – 14 Aug 2026 | Web: https://safal-events.vercel.app/
APPROVAL | RSVP Approval Workflow | FEAT-APPROVAL-03 | Approval emails, status & history | US-APPROVAL-007 | As a host or permitted staff, I want to a complete chronological record of all RSVP activity for an event, so that I have a full, auditable trail. | Medium | Developer 2 | S4 | Sprint 4 · 03 Aug 2026 – 14 Aug 2026 | Web: https://safal-events.vercel.app/
STAFF | Staff, Roles & Permissions | FEAT-STAFF-01 | Invite & manage staff | US-STAFF-001 | As a host (or staff with Manage Staff permission), I want to invite a team member by email and assign them a role for my event, so that others can help run the event with the right access. | High | Developer 3 | S7 | Sprint 7 · 14 Sep 2026 – 25 Sep 2026 | Web: https://safal-events.vercel.app/
STAFF | Staff, Roles & Permissions | FEAT-STAFF-01 | Invite & manage staff | US-STAFF-004 | As a staff member, I want to accept my invite and access only the event(s) I was invited to, so that I get straight to my assigned work. | Medium | Developer 3 | S7 | Sprint 7 · 14 Sep 2026 – 25 Sep 2026 | Web: https://safal-events.vercel.app/
STAFF | Staff, Roles & Permissions | FEAT-STAFF-01 | Invite & manage staff | US-STAFF-005 | As a host, I want to remove a staff member or change their role, so that I keep the team and its access current. | Medium | Developer 3 | S7 | Sprint 7 · 14 Sep 2026 – 25 Sep 2026 | Web: https://safal-events.vercel.app/
STAFF | Staff, Roles & Permissions | FEAT-STAFF-02 | Roles & permissions (RBAC) | US-STAFF-002 | As a host, I want to create/edit named roles by toggling permissions for every screen and action, so that I grant exactly the access each helper needs. | High | Developer 4 | S7 | Sprint 7 · 14 Sep 2026 – 25 Sep 2026 | Web: https://safal-events.vercel.app/
STAFF | Staff, Roles & Permissions | FEAT-STAFF-02 | Roles & permissions (RBAC) | US-STAFF-003 | As a staff member, I want to see only the tabs and actions my role permits, so that I can do exactly my job and nothing more. | High | Developer 4 | S7 | Sprint 7 · 14 Sep 2026 – 25 Sep 2026 | Web: https://safal-events.vercel.app/
CHECKIN | Gate Check-in & QR Scanner | FEAT-CHECKIN-01 | QR Scanner role & gate check-in | US-CHECKIN-001 | As a host, I want to assign a role whose only screen is gate Check-in, so that door staff can scan without seeing guest editing, messaging or settings. | Medium | Developer 5 | S5 | Sprint 5 · 17 Aug 2026 – 28 Aug 2026 | Web: https://safal-events.vercel.app/
CHECKIN | Gate Check-in & QR Scanner | FEAT-CHECKIN-01 | QR Scanner role & gate check-in | US-CHECKIN-002 | As a gate staff, I want to scan a guest's QR / pass and have it validated against the event's approved guests, so that only valid, approved guests are admitted. | High | Developer 5 | S5 | Sprint 5 · 17 Aug 2026 – 28 Aug 2026 | Web: https://safal-events.vercel.app/
CHECKIN | Gate Check-in & QR Scanner | FEAT-CHECKIN-01 | QR Scanner role & gate check-in | US-CHECKIN-003 | As a host (beneficiary), I want to each scan to update counts, notify and be logged, so that I see real-time turnout and have an audit trail. | Medium | Developer 5 | S5 | Sprint 5 · 17 Aug 2026 – 28 Aug 2026 | Web: https://safal-events.vercel.app/
MSG | Per-Event Messaging | FEAT-MSG-01 | Per-event messaging config & threads | US-MSG-001 | As a host, I want to turn guest messaging on or off for a specific event, so that I control whether guests can message me for each event. | Medium | Developer 1 | S6 | Sprint 6 · 31 Aug 2026 – 11 Sep 2026 | Web: https://safal-events.vercel.app/
MSG | Per-Event Messaging | FEAT-MSG-01 | Per-event messaging config & threads | US-MSG-002 | As a guest, I want to message the host in-app for an event that allows it and see replies, so that I can ask questions and get answers. | Medium | Developer 1 | S6 | Sprint 6 · 31 Aug 2026 – 11 Sep 2026 | Web: https://safal-events.vercel.app/
MSG | Per-Event Messaging | FEAT-MSG-01 | Per-event messaging config & threads | US-MSG-003 | As a staff member, I want to read and reply to guest messages only if my role allows it, so that messaging access matches my responsibilities. | Low | Developer 1 | S6 | Sprint 6 · 31 Aug 2026 – 11 Sep 2026 | Web: https://safal-events.vercel.app/
ACCESS | Account Types: Signup & Login | FEAT-ACCESS-01 | Signup account types (Guest/Host) | US-ACCESS-001 | As a new user, I want to clearly choose to register as a Guest or as a Host, so that I land in the right experience for what I want to do. | High | Developer 2 | S1 | Sprint 1 · 22 Jun 2026 – 03 Jul 2026 | Web: https://safal-events.vercel.app/
ACCESS | Account Types: Signup & Login | FEAT-ACCESS-02 | Unified login & staff invite login | US-ACCESS-002 | As a registered Host or Guest, I want to log in with email or phone and be taken to the correct flow, so that one simple login does the right thing. | High | Developer 3 | S1 | Sprint 1 · 22 Jun 2026 – 03 Jul 2026 | Web: https://safal-events.vercel.app/
ACCESS | Account Types: Signup & Login | FEAT-ACCESS-02 | Unified login & staff invite login | US-ACCESS-003 | As a invited staff member, I want to a 'Login as Staff' path where I enter my Invite ID and email/phone, so that I reach my assigned event with only my role's screens. | High | Developer 3 | S1 | Sprint 1 · 22 Jun 2026 – 03 Jul 2026 | Web: https://safal-events.vercel.app/
MOBILE | Mobile App (Browse-before-login & Parity) | FEAT-MOBILE-01 | Guest Mode browse & gated auth | US-MOBILE-001 | As a newly installed user, I want to explore the app without logging in or registering, so that I get a feel for it before committing to an account. | High | Developer 4 | S9 | Sprint 9 · 12 Oct 2026 – 23 Oct 2026 | Web: https://safal-events.vercel.app/
MOBILE | Mobile App (Browse-before-login & Parity) | FEAT-MOBILE-01 | Guest Mode browse & gated auth | US-MOBILE-002 | As a guest-mode user, I want to be sent to Login/Register only when I tap something that needs an account, so that I'm never blocked until it's actually necessary. | High | Developer 4 | S9 | Sprint 9 · 12 Oct 2026 – 23 Oct 2026 | Web: https://safal-events.vercel.app/
MOBILE | Mobile App (Browse-before-login & Parity) | FEAT-MOBILE-01 | Guest Mode browse & gated auth | US-MOBILE-003 | As a guest-mode user, I want to be brought back to the exact action I tapped after I authenticate, so that the flow feels seamless and I don't lose my place. | High | Developer 4 | S9 | Sprint 9 · 12 Oct 2026 – 23 Oct 2026 | Web: https://safal-events.vercel.app/
MOBILE | Mobile App (Browse-before-login & Parity) | FEAT-MOBILE-02 | Post-auth routing & sessions | US-MOBILE-004 | As a authenticated user, I want to be routed to my role's experience after signing in, so that I see what's relevant to me. | High | Developer 5 | S9 | Sprint 9 · 12 Oct 2026 – 23 Oct 2026 | Web: https://safal-events.vercel.app/
MOBILE | Mobile App (Browse-before-login & Parity) | FEAT-MOBILE-02 | Post-auth routing & sessions | US-MOBILE-005 | As a returning or linked user, I want to a discoverable login entry, a remembered session, and deep links that respect gating, so that returning and shared-link journeys are smooth. | Medium | Developer 5 | S9 | Sprint 9 · 12 Oct 2026 – 23 Oct 2026 | Web: https://safal-events.vercel.app/
MOBILE | Mobile App (Browse-before-login & Parity) | FEAT-MOBILE-03 | Host/Guest/Staff parity & phone-frame web | US-MOBILE-006 | As a any user, I want to the mobile app to mirror the web feature set, so that I can run everything from my phone. | Medium | Developer 1 | S9 | Sprint 9 · 12 Oct 2026 – 23 Oct 2026 | Web: https://safal-events.vercel.app/
MOBILE | Mobile App (Browse-before-login & Parity) | FEAT-MOBILE-03 | Host/Guest/Staff parity & phone-frame web | US-MOBILE-007 | As a reviewer, I want to open the mobile app in a browser and have it look like a phone, so that I can preview the mobile UI without a device. | Low | Developer 1 | S9 | Sprint 9 · 12 Oct 2026 – 23 Oct 2026 | Web: https://safal-events.vercel.app/
PLAT | Platform & Cross-Cutting | FEAT-PLAT-01 | Audit logging & OTP security | US-PLAT-001 | As a platform owner, I want to critical actions to be automatically written to an append-only audit trail, so that the platform is accountable and traceable. | Medium | Developer 2 | S1 | Sprint 1 · 22 Jun 2026 – 03 Jul 2026 | Web: https://safal-events.vercel.app/
PLAT | Platform & Cross-Cutting | FEAT-PLAT-01 | Audit logging & OTP security | US-PLAT-002 | As a platform owner, I want to one-time codes to expire, limit attempts and be fully logged, so that verification is secure against brute force and reuse. | High | Developer 2 | S1 | Sprint 1 · 22 Jun 2026 – 03 Jul 2026 | Web: https://safal-events.vercel.app/
PLAT | Platform & Cross-Cutting | FEAT-PLAT-02 | RBAC, responsive UI & persistence | US-PLAT-003 | As a platform owner, I want to each role to see only the screens and actions appropriate to it, so that users cannot access unauthorized functions. | High | Developer 3 | S1 | Sprint 1 · 22 Jun 2026 – 03 Jul 2026 | Web: https://safal-events.vercel.app/
PLAT | Platform & Cross-Cutting | FEAT-PLAT-02 | RBAC, responsive UI & persistence | US-PLAT-004 | As a any user, I want to a responsive interface that works on desktop and mobile with event themes, so that I have a good experience on any device. | Medium | Developer 3 | S1 | Sprint 1 · 22 Jun 2026 – 03 Jul 2026 | Web: https://safal-events.vercel.app/
PLAT | Platform & Cross-Cutting | FEAT-PLAT-02 | RBAC, responsive UI & persistence | US-PLAT-005 | As a any user, I want to my data (events, RSVPs, settings) to persist across sessions, so that I don't lose my work or registrations. | High | Developer 3 | S1 | Sprint 1 · 22 Jun 2026 – 03 Jul 2026 | Web: https://safal-events.vercel.app/
UIPRICE | Pricing, Subscription & Billing UI | FEAT-UI-01 | Landing pricing page | US-UI-001 | As a visitor, I want a clear pricing page with Individual/Organization and Monthly/Annual toggles, so that I can compare plans and choose one. | High | Developer 1 | S10 | Sprint 10 · 26 Oct 2026 – 06 Nov 2026 | Web: https://safal-events.vercel.app/
UIPRICE | Pricing, Subscription & Billing UI | FEAT-UI-02 | Host billing & subscription dashboard | US-UI-002 | As a host, I want to see my plan, usage and upgrade options, so that I understand my limits and how to upgrade. | High | Developer 2 | S10 | Sprint 10 · 26 Oct 2026 – 06 Nov 2026 | Web: https://safal-events.vercel.app/
UIPRICE | Pricing, Subscription & Billing UI | FEAT-UI-03 | Admin pricing & subscription console | US-UI-003 | As a superadmin, I want to manage plans, top-ups and host subscriptions centrally, so that I can run platform economics and support hosts. | High | Developer 1 | S10 | Sprint 10 · 26 Oct 2026 – 06 Nov 2026 | Web: https://safal-events.vercel.app/
UIPRICE | Pricing, Subscription & Billing UI | FEAT-UI-04 | Photo upload permission alignment | US-UI-004 | As a host, I want photo permissions grouped clearly in event settings and pricing, so that I understand and control photo features. | Medium | Developer 2 | S10 | Sprint 10 · 26 Oct 2026 – 06 Nov 2026 | Web: https://safal-events.vercel.app/
AGE | Age Restriction & Additional Guest Details | FEAT-AGE-01 | Configure age restriction | US-EVENT-013 | As a host, I want to toggle an age restriction and set a minimum age, so that only eligible guests attend. | High | Developer 1 | S10 | Sprint 10 · 26 Oct 2026 – 06 Nov 2026 | Web: https://safal-events.vercel.app/
AGE | Age Restriction & Additional Guest Details | FEAT-AGE-02 | DOB collection at RSVP | US-EVENT-014 | As a guest RSVPing to an age-restricted event, I want to enter my date of birth, so that the platform verifies I meet the age requirement. | High | Developer 2 | S10 | Sprint 10 · 26 Oct 2026 – 06 Nov 2026 | Web: https://safal-events.vercel.app/
AGE | Age Restriction & Additional Guest Details | FEAT-AGE-03 | Additional guest name + DOB | US-EVENT-015 | As a guest adding extra guests, I want to enter each guest's details, so that the host has a complete, age-compliant manifest. | High | Developer 1 | S10 | Sprint 10 · 26 Oct 2026 – 06 Nov 2026 | Web: https://safal-events.vercel.app/
AGE | Age Restriction & Additional Guest Details | FEAT-AGE-04 | Host view of guest ages | US-EVENT-016 | As a host, I want to see ages and party members of my guests, so that I can verify compliance at the door. | Medium | Developer 2 | S10 | Sprint 10 · 26 Oct 2026 – 06 Nov 2026 | Web: https://safal-events.vercel.app/
AGE | Age Restriction & Additional Guest Details | FEAT-AGE-05 | QR pass & check-in age verification | US-EVENT-017 | As gate staff, I want an at-a-glance age indicator, so that I can approve entry quickly. | Medium | Developer 1 | S10 | Sprint 10 · 26 Oct 2026 – 06 Nov 2026 | Web: https://safal-events.vercel.app/
PHOTO | Event Photo Album | FEAT-PHOTO-01 | Enable & configure album | US-PHOTO-001 | As a host, I want to enable a shared photo album with upload permissions, so that guests can relive the event. | High | Developer 2 | S10 | Sprint 10 · 26 Oct 2026 – 06 Nov 2026 | Web: https://safal-events.vercel.app/
PHOTO | Event Photo Album | FEAT-PHOTO-02 | Host album management & moderation | US-PHOTO-002 | As a host, I want to manage album photos, so that I keep content appropriate. | High | Developer 1 | S10 | Sprint 10 · 26 Oct 2026 – 06 Nov 2026 | Web: https://safal-events.vercel.app/
PHOTO | Event Photo Album | FEAT-PHOTO-03 | Guest view & upload | US-PHOTO-003 | As a guest, I want to view and (when allowed) add photos, so that I can share my perspective. | Medium | Developer 2 | S10 | Sprint 10 · 26 Oct 2026 – 06 Nov 2026 | Web: https://safal-events.vercel.app/
BRAND | Platform Consistency & Branding | FEAT-BRAND-01 | Theme consistency across roles | US-PLAT-001 | As a user of any role, I want colors/fonts to stay correct after switching or logging out, so that the UI is consistent. | High | Developer 1 | S10 | Sprint 10 · 26 Oct 2026 – 06 Nov 2026 | Web: https://safal-events.vercel.app/
BRAND | Platform Consistency & Branding | FEAT-BRAND-02 | Role-aware dashboard top bar | US-PLAT-002 | As a signed-in user, I want key controls on top of my dashboard, so that I can see my plan and act quickly. | Medium | Developer 2 | S10 | Sprint 10 · 26 Oct 2026 – 06 Nov 2026 | Web: https://safal-events.vercel.app/
BRAND | Platform Consistency & Branding | FEAT-BRAND-03 | Updated logo lockup | US-PLAT-003 | As a user, I want the new logo presented well, so that branding is clear. | Low | Developer 1 | S10 | Sprint 10 · 26 Oct 2026 – 06 Nov 2026 | Web: https://safal-events.vercel.app/

## Sprint Summary
Sprint | Timeline | Epics in sprint | # Features | # User Stories
S1 | Sprint 1 · 22 Jun 2026 – 03 Jul 2026 | Authentication & Host Onboarding (AUTH), Account Types: Signup & Login (ACCESS), Platform & Cross-Cutting (PLAT) | 8 | 15
S2 | Sprint 2 · 06 Jul 2026 – 17 Jul 2026 | Event Creation & Management (Host) (EVENT) | 5 | 12
S3 | Sprint 3 · 20 Jul 2026 – 31 Jul 2026 | Event Discovery (Guest) (DISC), RSVP & Ticketing (Guest) (RSVP) | 7 | 15
S4 | Sprint 4 · 03 Aug 2026 – 14 Aug 2026 | RSVP Approval Workflow (APPROVAL), Guest Dashboard & Self-Service (GUEST) | 7 | 14
S5 | Sprint 5 · 17 Aug 2026 – 28 Aug 2026 | Guest Management & Check-in (Host) (GM), Gate Check-in & QR Scanner (CHECKIN) | 5 | 9
S6 | Sprint 6 · 31 Aug 2026 – 11 Sep 2026 | Notifications & Templates Engine (NOTIF), Per-Event Messaging (MSG) | 5 | 11
S7 | Sprint 7 · 14 Sep 2026 – 25 Sep 2026 | Staff, Roles & Permissions (STAFF), Payments & Payouts (Host) (PAY) | 4 | 10
S8 | Sprint 8 · 28 Sep 2026 – 09 Oct 2026 | Engagement (Comments, Polls, Photos) (ENG), Analytics & Reporting (Host) (ANALYTICS), Admin Console (ADMIN) | 9 | 17
S9 | Sprint 9 · 12 Oct 2026 – 23 Oct 2026 | Mobile App (Browse-before-login & Parity) (MOBILE) | 3 | 7

## Read me
SafalEvents — Sprint Planning
Product
SafalEvents — event hosting, RSVP & ticketing platform (web + mobile).
Live mockup / prototype URL
Web: https://safal-events.vercel.app/
How to use
Sheet 'Sprint Plan' = one row per user story, grouped Epic -> Feature -> User Story.
Sheet 'Sprint Summary' = sprint timeline overview.
Use the header filters on the Sprint Plan sheet to slice by Epic, Sprint, Priority or Developer.
Notes
'Developer Assigned' values are placeholders (round-robin) — replace with your team.
Sprints are 2 weeks; the schedule starts 22 Jun 2026 and is a suggested sequence by dependency.
Story/epic content is the single source of truth shared with SafalEvents_User_Stories.docx.